## Communication Plan
Communication Plan – Gaming with RL Feature
Comm. ID | Communication Type | Purpose | Audience / Stakeholders | Owner | Channel / Method | Frequency / Timing | Format / Output | Escalation / Follow-up | Records / Evidence
CP-01 | Daily Team Check-in | Discuss current tasks, blockers, and short-term priorities. | All team members | Shafan | WhatsApp / in-person / quick call | Daily during active build periods | Short verbal update | Unresolved blockers raised in weekly review | Chat messages / brief notes
CP-02 | Weekly Sprint Review Meeting | Review sprint progress against tasks, milestones, and deadlines. | All team members | Shafan | Face-to-face meeting / Microsoft Teams | Weekly | Agenda + action list | 9 | Meeting notes / updated sprint sheet
CP-03 | Technical Coordination | Coordinate Python RL, game logic, Unity integration, and testing dependencies. | Shafan, Abdullah, Ahmed | Abdullah | In-person discussion / shared files / chat | 2–3 times per week as needed | Task update / technical notes | Open bugs logged and reviewed in team meeting | Shared docs / version notes
CP-04 | Documentation Review | Check reports, charts, evidence, and academic documents before submission. | Ahmed + team | Ahmed | Google Docs / Word / in-person review | Weekly and before each submission | Reviewed draft | Major gaps returned for revision | Revised files / review comments
CP-05 | Testing and Evaluation Update | Share test results, bug findings, model performance, and evaluation metrics. | All team members | Ahmed | Excel sheets / screenshots / discussion | After major testing sessions | Test summary | Critical defects prioritised for immediate fix | Test logs / screenshots / metrics tables
CP-06 | Presentation Planning | Prepare speaking order, slide responsibilities, demo flow, and rehearsal tasks. | All team members | Ahmed | Meeting + PowerPoint review | Near milestone demos and final presentation phase | Presentation checklist | Missed items assigned to owner before rehearsal | Slide deck / rehearsal notes
CP-07 | GitHub / File Update Notice | Inform team when major code, design, or documents are added or changed. | All team members | Owner of file/task | WhatsApp / GitHub / shared folder | Whenever significant updates occur | Short update message | Version conflicts discussed in next meeting | Commit history / shared file timestamps
CP-08 | Risk / Issue Escalation | Highlight risks such as delays, integration problems, bugs, or missing evidence. | Relevant team members + supervisor if needed | Shafan | Meeting / direct message | As required | Issue note + proposed action | Escalate to supervisor when team cannot resolve internally | Risk log
CP-09 | Final Submission Confirmation | Confirm final versions, submission ownership, and upload deadlines. | All team members | Ahmed | Meeting + WhatsApp confirmation | Before each assessment submission | Submission checklist | Any missing item resolved same day | Final copies / screenshots of upload