## Gantt Chart
Gantt Chart – Gaming with RL Feature
ID | Task | Owner(s) | Start Date | End Date | Duration (days) | Dependency | Status | % Complete | 31-Oct | 07-Nov | 14-Nov | 21-Nov | 28-Nov | 05-Dec | 12-Dec | 19-Dec | 26-Dec | 02-Jan | 09-Jan | 16-Jan | 23-Jan | 30-Jan | 06-Feb | 13-Feb | 20-Feb | 27-Feb | 06-Mar | 13-Mar | 20-Mar | 27-Mar | 03-Apr
Initiation and Planning
G-01 | Project kickoff | All Team Members | 31-Oct-2025 | 03-Nov-2025 | 4 | - | Completed | 100% | bar: 31-Oct
G-02 | Gather requirements | Ahmed / Shafan | 01-Nov-2025 | 07-Nov-2025 | 7 | G-01 | Completed | 100%
G-03 | Scope finalization | Ahmed / Shafan | 05-Nov-2025 | 10-Nov-2025 | 6 | G-02 | Completed | 100% | bar: 31-Oct to 07-Nov
G-04 | Research and literature review | All Team Members | 06-Nov-2025 | 15-Nov-2025 | 10 | G-02 | Completed | 100%
G-05 | System architecture design | Shafan / Abdullah | 12-Nov-2025 | 20-Nov-2025 | 9 | G-03,G-04 | Completed | 100% | bar: 07-Nov to 14-Nov
M-01 | Milestone: Planning complete | All Team Members | 20-Nov-2025 | 20-Nov-2025 | 1 | G-05 | Completed | 100% | bar: 31-Oct to 03-Apr
Game Design and Environment Setup
G-06 | UI design and gameplay concept alignment | Abdullah | 10-Nov-2025 | 21-Nov-2025 | 12 | G-03 | Completed | 100%
G-07 | RL environment setup | Shafan | 15-Nov-2025 | 25-Nov-2025 | 11 | G-04 | Completed | 100% | bar: 14-Nov to 21-Nov
G-08 | Unity project setup | Abdullah | 15-Nov-2025 | 26-Nov-2025 | 12 | G-06 | Completed | 100%
G-09 | Documentation setup and planning evidence | Ahmed | 15-Nov-2025 | 27-Nov-2025 | 13 | G-03 | Completed | 100% | bar: 14-Nov to 21-Nov
M-02 | Milestone: Environment ready | All Team Members | 27-Nov-2025 | 27-Nov-2025 | 1 | G-07,G-08,G-09 | Completed | 100% | bar: 31-Oct to 03-Apr
RL Model Devlopment
G-10 | Q-learning environment design | Shafan | 21-Nov-2025 | 05-Dec-2025 | 15 | M-01 | Completed | 100%
G-11 | DQN environment and agent setup | Shafan | 01-Dec-2025 | 20-Dec-2025 | 20 | G-10 | Completed | 100% | bar: 28-Nov to 19-Dec
G-12 | State, action, and reward design | Shafan | 24-Nov-2025 | 12-Dec-2025 | 19 | G-07 | Completed | 100%
G-13 | RL training and tuning | Shafan | 10-Dec-2025 | 05-Jan-2026 | 27 | G-11,G-12 | Completed | 100% | bar: 05-Dec to 02-Jan
G-14 | Backend game logic and rule validation | Shafan | 21-Nov-2025 | 05-Jan-2026 | 46 | M-01 | Completed | 100%
M-03 | Milestone: RL model development complete | All Team Members | 05-Jan-2026 | 05-Jan-2026 | 1 | G-10:G-14 | Completed | 100% | bar: 02-Jan
Unity development and Integration
G-15 | Unity UI implementation | Abdullah | 28-Nov-2025 | 20-Dec-2025 | 23 | G-08 | Completed | 100% | bar: 28-Nov to 19-Dec
G-16 | Gameplay coding in Unity | Abdullah | 05-Dec-2025 | 20-Jan-2026 | 47 | G-15 | Completed | 100%
G-17 | Python–Unity integration support | Abdullah / Shafan | 10-Jan-2026 | 10-Feb-2026 | 32 | G-13,G-16 | Completed | 100% | bar: 09-Jan to 06-Feb
G-18 | Unity UI fixes and improvements | Abdullah | 01-Feb-2026 | 10-Mar-2026 | 38 | G-16 | Completed | 100%
M-04 | Milestone: Unity and integration complete | All Team Members | 10-Mar-2026 | 10-Mar-2026 | 1 | G-17,G-18 | Completed | 100% | bar: 06-Mar
Testing and Performance Tuning
G-19 | Automated backend testing | Shafan / Ahmed | 06-Jan-2026 | 10-Feb-2026 | 36 | M-03 | Completed | 100% | bar: 02-Jan to 06-Feb
G-20 | Manual gameplay testing | Ahmed / Abdullah | 15-Jan-2026 | 20-Feb-2026 | 37 | G-16 | Completed | 100%
G-21 | Integration testing | Ahmed / Abdullah / Shafan | 20-Jan-2026 | 25-Feb-2026 | 37 | G-17 | Completed | 100% | bar: 16-Jan to 20-Feb
G-22 | Performance tuning and debugging | All Team Members | 25-Jan-2026 | 28-Feb-2026 | 35 | G-19,G-20,G-21 | Completed | 100%
G-23 | Evaluation metrics and validation | Ahmed | 01-Feb-2026 | 28-Feb-2026 | 28 | G-19 | Completed | 100% | bar: 30-Jan to 27-Feb
M-05 | Milestone: Testing and tuning complete | All Team Members | 28-Feb-2026 | 28-Feb-2026 | 1 | G-19:G-23 | Completed | 100% | bar: 31-Oct to 03-Apr
UI, Documentation and Delivery
G-24 | User interface polish and visualization | Abdullah | 01-Mar-2026 | 20-Mar-2026 | 20 | M-04 | Completed | 100%
G-25 | Technical documentation and reports | Ahmed | 01-Mar-2026 | 25-Mar-2026 | 25 | M-05 | Completed | 100% | bar: 27-Feb to 20-Mar
G-26 | Quality review and status reporting | Ahmed / All Team Members | 10-Mar-2026 | 27-Mar-2026 | 18 | G-25 | Completed | 100%
G-27 | Presentation and demo preparation | Ahmed / All Team Members | 18-Mar-2026 | 02-Apr-2026 | 16 | G-24,G-25 | Completed | 100% | bar: 13-Mar to 27-Mar
G-28 | Final fixes and submission review | All Team Members | 21-Mar-2026 | 03-Apr-2026 | 14 | G-26,G-27 | Completed | 100%
M-06 | Milestone: Final delivery complete | All Team Members | 03-Apr-2026 | 03-Apr-2026 | 1 | G-28 | Completed | 100% | bar: 03-Apr
Milestone Summary
Milestone ID | Milestone Phase | Date | Linked Deliverable | Status | % Complete
M-01 | Planning Complete | 20-Nov-2025 | Approved direction, scope, and architecture basis | Completed | 100%
M-02 | Environment Ready | 27-Nov-2025 | RL and Unity setup base ready | Completed | 100%
M-03 | RL model development complete | 05-Jan-2026 | Q-learning/DQN setup and backend rule base complete | Completed | 100%
M-04 | Unity and integration complete | 10-Mar-2026 | Playable Unity side and integration support ready | Completed | 100%
M-05 | Testing and tuning complete | 28-Feb-2026 | Testing, debugging, metrics, and validation complete | Completed | 100%
M-06 | Final Delivery complete | 03-Apr-2026 | Reports, review, presentation prep, and final readiness complete | Completed | 100%

## Task Register
Detailed Task Register
Task ID | Phase | Task | Owner(s) | Start Date | End Date | Duration (days) | Dependency | Status
G-01 | 1. Initiation & Planning | Project kickoff | All Team Members | 31-Oct-2025 | 03-Nov-2025 | 4 | - | Completed
G-02 | 1. Initiation & Planning | Gather requirements | Ahmed / Shafan | 01-Nov-2025 | 07-Nov-2025 | 7 | G-01 | Completed
G-03 | 1. Initiation & Planning | Scope finalization | Ahmed / Shafan | 05-Nov-2025 | 10-Nov-2025 | 6 | G-02 | Completed
G-04 | 1. Initiation & Planning | Research and literature review | All Team Members | 06-Nov-2025 | 15-Nov-2025 | 10 | G-02 | Completed
G-05 | 1. Initiation & Planning | System architecture design | Shafan / Abdullah | 12-Nov-2025 | 20-Nov-2025 | 9 | G-03,G-04 | Completed
M-01 | 1. Initiation & Planning | Milestone: Planning complete | All Team Members | 20-Nov-2025 | 20-Nov-2025 | 1 | G-05 | Completed
G-06 | 2. Game Design & Environment Setup | UI design and gameplay concept alignment | Abdullah | 10-Nov-2025 | 21-Nov-2025 | 12 | G-03 | Completed
G-07 | 2. Game Design & Environment Setup | RL environment setup | Shafan | 15-Nov-2025 | 25-Nov-2025 | 11 | G-04 | Completed
G-08 | 2. Game Design & Environment Setup | Unity project setup | Abdullah | 15-Nov-2025 | 26-Nov-2025 | 12 | G-06 | Completed
G-09 | 2. Game Design & Environment Setup | Documentation setup and planning evidence | Ahmed | 15-Nov-2025 | 27-Nov-2025 | 13 | G-03 | Completed
M-02 | 2. Game Design & Environment Setup | Milestone: Environment ready | All Team Members | 27-Nov-2025 | 27-Nov-2025 | 1 | G-07,G-08,G-09 | Completed
G-10 | 3. RL Model Development | Q-learning environment design | Shafan | 21-Nov-2025 | 05-Dec-2025 | 15 | M-01 | Completed
G-11 | 3. RL Model Development | DQN environment and agent setup | Shafan | 01-Dec-2025 | 20-Dec-2025 | 20 | G-10 | Completed
G-12 | 3. RL Model Development | State, action, and reward design | Shafan | 24-Nov-2025 | 12-Dec-2025 | 19 | G-07 | Completed
G-13 | 3. RL Model Development | RL training and tuning | Shafan | 10-Dec-2025 | 05-Jan-2026 | 27 | G-11,G-12 | Completed
G-14 | 3. RL Model Development | Backend game logic and rule validation | Shafan | 21-Nov-2025 | 05-Jan-2026 | 46 | M-01 | Completed
M-03 | 3. RL Model Development | Milestone: RL model development complete | All Team Members | 05-Jan-2026 | 05-Jan-2026 | 1 | G-10:G-14 | Completed
G-15 | 4. Unity Development & Integration | Unity UI implementation | Abdullah | 28-Nov-2025 | 20-Dec-2025 | 23 | G-08 | Completed
G-16 | 4. Unity Development & Integration | Gameplay coding in Unity | Abdullah | 05-Dec-2025 | 20-Jan-2026 | 47 | G-15 | Completed
G-17 | 4. Unity Development & Integration | Python–Unity integration support | Abdullah / Shafan | 10-Jan-2026 | 10-Feb-2026 | 32 | G-13,G-16 | Completed
G-18 | 4. Unity Development & Integration | Unity UI fixes and improvements | Abdullah | 01-Feb-2026 | 10-Mar-2026 | 38 | G-16 | Completed
M-04 | 4. Unity Development & Integration | Milestone: Unity and integration complete | All Team Members | 10-Mar-2026 | 10-Mar-2026 | 1 | G-17,G-18 | Completed
G-19 | 5. Testing & Performance Tuning | Automated backend testing | Shafan / Ahmed | 06-Jan-2026 | 10-Feb-2026 | 36 | M-03 | Completed
G-20 | 5. Testing & Performance Tuning | Manual gameplay testing | Ahmed / Abdullah | 15-Jan-2026 | 20-Feb-2026 | 37 | G-16 | Completed
G-21 | 5. Testing & Performance Tuning | Integration testing | Ahmed / Abdullah / Shafan | 20-Jan-2026 | 25-Feb-2026 | 37 | G-17 | Completed
G-22 | 5. Testing & Performance Tuning | Performance tuning and debugging | All Team Members | 25-Jan-2026 | 28-Feb-2026 | 35 | G-19,G-20,G-21 | Completed
G-23 | 5. Testing & Performance Tuning | Evaluation metrics and validation | Ahmed | 01-Feb-2026 | 28-Feb-2026 | 28 | G-19 | Completed
M-05 | 5. Testing & Performance Tuning | Milestone: Testing and tuning complete | All Team Members | 28-Feb-2026 | 28-Feb-2026 | 1 | G-19:G-23 | Completed
G-24 | 6. UI, Documentation & Final Delivery | User interface polish and visualization | Abdullah | 01-Mar-2026 | 20-Mar-2026 | 20 | M-04 | Completed
G-25 | 6. UI, Documentation & Final Delivery | Technical documentation and reports | Ahmed | 01-Mar-2026 | 25-Mar-2026 | 25 | M-05 | Completed
G-26 | 6. UI, Documentation & Final Delivery | Quality review and status reporting | Ahmed / All Team Members | 10-Mar-2026 | 27-Mar-2026 | 18 | G-25 | Completed
G-27 | 6. UI, Documentation & Final Delivery | Presentation and demo preparation | Ahmed / All Team Members | 18-Mar-2026 | 02-Apr-2026 | 16 | G-24,G-25 | Completed
G-28 | 6. UI, Documentation & Final Delivery | Final fixes and submission review | All Team Members | 21-Mar-2026 | 03-Apr-2026 | 14 | G-26,G-27 | Completed
M-06 | 6. UI, Documentation & Final Delivery | Milestone: Final delivery complete | All Team Members | 03-Apr-2026 | 03-Apr-2026 | 1 | G-28 | Completed