## Product Backlog
Product Backlog – Gaming with RL Feature
Project Goal |  |  | Timeline |  |  | Core Team |  |  | Current Scope
Develop a working RL-based game with an AI agent targeting at least 80% success. |  |  | 31 Oct 2025 – 03 Apr 2026 |  |  | Shafan, Abdullah, Ahmed |  |  | RL model, Unity game, testing, documentation, final demo
Backlog ID | Epic | User Story / Backlog Item | Priority | Story Points | Owner | Support | Milestone / Phase | Target Period | Start Date | End Date | Status | Acceptance Criteria | Main Deliverable
PB-01 | Project Initiation | Define the game vision, problem statement, and project objectives for the RL-based game. | High | 3 | Shafan | Ahmed | Game Design & Environment Setup | Week 1 | 2025-10-31 | 2025-11-03 | Done | Project aim, scope, and success criteria are agreed by the team. | Project kickoff pack
PB-02 | Requirements | Gather and document gameplay, AI, technical, and assessment requirements. | High | 5 | Ahmed | Shafan, Abdullah | Game Design & Environment Setup | Week 1 | 2025-11-01 | 2025-11-06 | Done | Core functional and non-functional requirements are written and reviewed. | Requirements draft
PB-03 | Planning | Define system architecture linking Python RL environment with Unity gameplay. | High | 5 | Shafan | Abdullah, Ahmed | Game Design & Environment Setup | Week 2 | 2025-11-04 | 2025-11-10 | Done | Architecture flow, tools, and component responsibilities are documented. | Architecture outline
PB-04 | Backlog Management | Create and prioritise the initial product backlog for all RL, Unity, testing, and documentation tasks. | High | 3 | Ahmed | Shafan, Abdullah | Game Design & Environment Setup | Week 2 | 2025-11-05 | 2025-11-10 | Done | Backlog items are prioritised and linked to milestones. | Initial backlog
PB-05 | Research | Research RL algorithms, Unity tools, testing methods, and integration options. | High | 5 | Shafan | Abdullah, Ahmed | Game Design & Environment Setup | Weeks 2-3 | 2025-11-06 | 2025-11-14 | Done | Relevant methods and tools are compared and selected. | Research summary
PB-06 | Game Design | Formalise game rules, board structure, win/loss conditions, and gameplay mechanics. | High | 8 | Shafan | Abdullah | Game Design & Environment Setup | Weeks 2-3 | 2025-11-07 | 2025-11-18 | Done | Rules are clear enough to implement consistently in Python and Unity. | Rules and logic draft
PB-07 | Unity Design | Create the initial UI concept, board layout plan, and Unity environment setup. | High | 5 | Abdullah | Ahmed | Game Design & Environment Setup | Week 3 | 2025-11-10 | 2025-11-20 | Done | Unity project structure and base visual design are ready. | Unity setup ready
PB-08 | RL Environment | Build the RL training environment and state/action representation. | High | 8 | Shafan | Ahmed | RL Model Development | Sprint A | 2025-11-21 | 2025-12-05 | Done | Environment supports reset, step, valid actions, and reward flow. | RL environment module
PB-09 | Game Logic | Implement game logic, rules, board classes, and reusable functions. | High | 8 | Shafan | Abdullah | RL Model Development | Sprint A | 2025-11-21 | 2025-12-10 | Done | Core classes and rule functions execute expected moves and outcomes. | Game logic module
PB-10 | Unity Development | Develop the playable Unity board, piece placement, and basic interactions. | High | 8 | Abdullah | Ahmed | RL Model Development | Sprint A | 2025-11-24 | 2025-12-12 | Done | User can see the board and interact with pieces in Unity. | Playable prototype
PB-11 | AI Model Setup | Set up Q-learning baseline and DQN training pipeline. | High | 8 | Shafan | Ahmed | RL Model Development | Sprint B | 2025-12-01 | 2025-12-20 | Done | Training pipeline runs with baseline metrics and saved checkpoints. | Q-learning and DQN setup
PB-12 | Integration | Integrate RL outputs with gameplay flow and align RL logic with UI behaviour. | High | 8 | Shafan | Abdullah | RL Model Development | Sprint B | 2025-12-08 | 2025-12-22 | Done | AI decisions map correctly to valid game moves and turn flow. | Initial RL-Unity integration
PB-13 | Testing Preparation | Define testing checklist, evaluation metrics, and evidence capture process. | Medium | 3 | Ahmed | Shafan | RL Model Development | Sprint B | 2025-12-08 | 2025-12-18 | Done | Test cases, metric definitions, and reporting method are agreed. | Testing plan draft
PB-14 | Debugging | Fix early RL errors, UI bugs, and integration issues from prototype tests. | High | 5 | Abdullah | Shafan, Ahmed | Testing & Performance Tuning | Sprint C | 2026-01-06 | 2026-01-20 | Done | Critical defects are logged, resolved, and re-tested. | Stable core build
PB-15 | Model Improvement | Tune RL rewards, policies, and hyperparameters to improve learning results. | High | 8 | Shafan | Ahmed | Testing & Performance Tuning | Sprint C | 2026-01-06 | 2026-02-05 | Done | Model performance improves against baseline tests and target metrics. | Improved RL model
PB-16 | UI Enhancement | Improve game interface, feedback, and interaction quality in Unity. | Medium | 5 | Abdullah | Ahmed | Testing & Performance Tuning | Sprint C | 2026-01-12 | 2026-02-10 | Done | UI becomes clearer, more stable, and easier to use. | Enhanced UI
PB-17 | System Integration | Complete end-to-end RL, Unity, and gameplay integration. | High | 8 | Abdullah | Shafan | Testing & Performance Tuning | Sprint D | 2026-01-20 | 2026-02-15 | Done | Full workflow runs from gameplay input to AI response without major breaks. | Integrated system
PB-18 | System Testing | Run functional, integration, and performance testing across the full system. | High | 8 | Ahmed | Shafan, Abdullah | Testing & Performance Tuning | Sprint D | 2026-02-01 | 2026-02-28 | Done | Testing evidence is collected and major issues are tracked. | Tested system
PB-19 | Validation & Metrics | Validate AI behaviour using evaluation metrics and compare against targets. | High | 5 | Ahmed | Shafan | Testing & Performance Tuning | Sprint D | 2026-02-05 | 2026-02-28 | Done | Evaluation confirms whether AI performance and stability meet expectations. | Validation report
PB-20 | Optimisation | Optimise RL tuning, Unity performance, and overall build stability. | Medium | 5 | Shafan | Abdullah, Ahmed | Testing & Performance Tuning | Sprint D | 2026-02-10 | 2026-02-28 | Done | Game performs smoothly and AI runs reliably. | Optimised build
PB-21 | Visualisation | Create visualisation of AI learning progress and performance outputs. | Medium | 3 | Ahmed | Shafan | User Interface & Visualisation | Sprint E | 2026-03-01 | 2026-03-10 | Done | Graphs, visuals, or status displays clearly show AI progress. | AI visualisation assets
PB-22 | UI Polish | Polish the final Unity interface and user experience for demonstration. | Medium | 5 | Abdullah | Ahmed | User Interface & Visualisation | Sprint E | 2026-03-01 | 2026-03-20 | Done | Final visuals are presentation-ready and consistent. | Presentation-ready UI
PB-23 | Documentation | Write the technical report sections covering RL, Unity, testing, and evaluation. | High | 5 | Ahmed | Shafan, Abdullah | Final Report, Presentation & Demo | Sprint F | 2026-03-21 | 2026-03-28 | Done | Draft report includes technical details, evidence, and clear structure. | Draft report
PB-24 | Final QA | Run final checks on AI, Unity, metrics, and documentation before submission. | High | 3 | Ahmed | Shafan, Abdullah | Final Report, Presentation & Demo | Sprint F | 2026-03-24 | 2026-04-01 | Done | All major issues are resolved or documented with mitigation. | Near-final package
PB-25 | Presentation Prep | Prepare the final demo, slide content, speaking points, and backup evidence. | High | 5 | Ahmed | Shafan, Abdullah | Final Report, Presentation & Demo | Sprint F | 2026-03-25 | 2026-04-03 | Done | Team can demonstrate the system and explain methods confidently. | Final presentation and demo

## Legend & Notes
Legend & Notes
Type | Value | Meaning
Priority | High | Critical work that strongly affects delivery or core functionality.
Priority | Medium | Important work that improves quality, usability, or evidence.
Story Points | 3 | Small task with limited complexity and lower effort.
Story Points | 5 | Medium task needing coordination or moderate implementation effort.
Story Points | 8 | Large or technically complex task with higher implementation effort.
Status | Done | Completed and evidenced in sprint work.
Status | In Progress | Started but still being developed, debugged, or integrated.
Status | To Do | Planned work that has not yet been completed.