## Quality Report
Quality Report – Gaming with RL Feature
Quality ID | Quality Area | Standard / Requirement | How Quality Was Checked | Owner(s) | Status | % Complete | Evidence | Quality Outcome | Notes
QR-01 | Project Planning | Planning documents should be clear, structured, and aligned with project aims. | Reviewed against charter, milestones, backlog, and sprint documents. | Ahmed / Shafan | Completed | 100% | Charter, budget, backlog, sprint files | Planning documentation completed to a consistent standard. | Core PM documents prepared
QR-02 | Requirements Alignment | Work should stay within project scope and agreed deliverables. | Compared work against project charter scope and milestones. | All Team Members | Completed | 100% | Project Charter / milestone docs | Project remained focused on core RL game scope. | Out-of-scope features avoided
QR-03 | Game Logic Quality | Python rules and game logic should match intended game behaviour. | Checked through automated tests and rule-based scenarios. | Shafan | Completed | 100% | Python code / test results | Game logic validated and consistent with interpreted rules. | Backend quality confirmed
QR-04 | RL Environment Quality | RL environment should return valid states, actions, rewards, and outputs. | Validated through environment tests and code review. | Shafan | Completed | 100% | OriginsEnv checks / automated tests | Environment quality supports Q-learning and DQN workflows. | AI pipeline quality maintained
QR-05 | Unity Quality | Unity interface and gameplay environment should function clearly and reliably. | Observed through implementation checks, UI review, and gameplay testing. | Abdullah | Completed | 100% | Unity project / gameplay observations | Playable front-end environment completed. | Frontend quality achieved
QR-06 | Integration Quality | Python and Unity sides should work together correctly for gameplay and state handling. | Checked using game-state export logic and integration review. | Abdullah / Shafan | Completed | 100% | Export test / integration checks | Integration quality considered and validated for project needs. | Cross-system consistency addressed
QR-07 | Testing Quality | Testing must be sufficient to support confidence in the prototype. | Used pytest, manual testing, and broader project-level checks. | Ahmed / Shafan / Abdullah | Completed | 100% | 23/23 tests passed + test plan | Testing quality is strong and supports final submission. | Automated + manual coverage
QR-08 | Documentation Quality | Reports and supporting documents should be clear, organised, and presentation-ready. | Reviewed for structure, consistency, and completeness. | Ahmed | Completed | 100% | Project reports and planning files | Documentation quality completed to submission standard. | Paperwork and evidence prepared
QR-09 | Evaluation Quality | Metrics and evaluation claims should be supported by test or project evidence. | Linked evaluation notes to test results and development outcomes. | Ahmed | Completed | 100% | Evaluation notes / test evidence | Evaluation reporting supported by available evidence. | Useful for report and demo
QR-10 | Presentation Quality | Presentation materials should be clear, organised, and ready for delivery. | Checked demo flow, project story, and supporting visuals. | Ahmed / All Team Members | Completed | 100% | Presentation files / demo prep | Presentation quality marked ready. | Supports final assessment
Quality Control Activities
QC ID | Activity | Description | Main Owner | Support | Status | Result / Outcome | Evidence | Frequency | Remarks
QC-01 | Document Review | Review planning and report documents for completeness and consistency. | Ahmed | All Team Members | Completed | Documents aligned and completed | Planning files / reports | Throughout project | Supports submission quality
QC-02 | Code Review | Check backend and gameplay code for logic, structure, and correctness. | Shafan / Abdullah | Ahmed | Completed | Code reviewed and refined | Source files / test evidence | During development | Improves reliability
QC-03 | Automated Testing | Run pytest tests to validate core rules and environment behaviour. | Shafan | Ahmed | Completed | 23/23 passed | pytest output | After logic updates | Strong formal check
QC-04 | Manual Gameplay Testing | Observe gameplay behaviour, UI responses, and flow across scenarios. | Abdullah | Ahmed | Completed | Gameplay quality confirmed | Manual test notes / screenshots | Before demo and after changes | Important for front-end validation
QC-05 | Integration Check | Check state export and gameplay support between Python and Unity. | Abdullah / Shafan | Ahmed | Completed | Integration support validated | Export checks / observed runs | During integration stage | Supports full prototype
QC-06 | Final Readiness Review | Confirm that deliverables are ready for final assessment stage. | Ahmed | All Team Members | Completed | Project package considered ready | Compiled documents / demo prep | Final stage | Final quality gate