## RACI Chart
RACI Chart – Gaming with RL Feature | [6 empty] | RACI Key
Activity ID | Project Activity | Shafan Shafqat | Abdullah Butt | Ahmed Saeed | Project Supervisor | Notes | A
RA1 | Define project scope and project objectives | A | C | C | I | Scope aligned with charter and module expectations | C
RA2 | Prepare project charter and initial planning documents | R | C | A | I | Ahmed leads documentation support | I
RA3 | Design game rules and logic structure | A/R | C | I | I | Core rule framework and system behaviour
RA4 | Develop Python game engine and class structure | A/R | I | C | I | Includes rules, functions, and core logic
RA5 | Set up RL environment for Q-learning and DQN | A/R | I | C | I | Shafan handles environment and agent setup
RA6 | Train and tune RL agents | A/R | I | C | I | Model tuning, learning behaviour, and experiments
RA7 | Unit testing of classes and functions | A/R | I | C | I | Testing of Python-side implementation
RA8 | Design Unity game interface and board layout | C | A/R | I | I | Unity visuals and interaction design
RA9 | Implement Unity game coding and mechanics | C | A/R | I | I | C# Unity coding and feature development
RA10 | Integrate Unity with AI/game backend | C | A/R | C | I | Connection between gameplay and model responses
RA11 | Support Unity setup and configuration | I | R | A | I | Ahmed supports setup and environment preparation
RA12 | Testing and evaluation of overall game | C | C | A/R | I | Functional testing and evaluation metrics
RA13 | Prepare documentation, reports, and paperwork | C | I | A/R | I | All written deliverables and documentation
RA14 | Track sprint progress and team communication | A | R | R | I | Shared agile coordination with Shafan leading
RA15 | Prepare final presentation and demo materials | C | C | A/R | I | Presentation assets, organisation, and reporting
R | Responsible | The person who does the work and completes the task.
A | Accountable | The person who owns the task and is answerable for the final outcome.
C | Consulted | The person who gives input, advice, or specialist support before decisions are made.
I | Informed | The person who is kept updated on progress or outcomes.