## Risk Assessment
Risk Assessment – Gaming with RL Feature
Risk ID | Risk Area | Risk Description | Probability | Impact | Risk Level | Mitigation Strategy | Contingency Plan | Owner | Status | Monitoring Method | Notes
R-01 | RL Development | The RL model may not learn effectively or may produce weak performance. | Medium | High | High | Start with simpler setups, validate state/action design, and tune rewards gradually. | Use a smaller prototype or fallback AI mode for demonstration. | Shafan | Managed | Evaluation metrics and training reviews | Linked to Q-learning/DQN work
R-02 | Time Management | The project may face time pressure because of coursework, documentation, and technical workload. | High | High | High | Split tasks clearly, use sprint planning, and monitor milestones regularly. | Re-prioritise non-essential work and focus on core deliverables first. | All Team Members | Managed | Sprint reviews and status tracking | Common academic project risk
R-03 | Unity Integration | Backend game logic and Unity gameplay may not integrate smoothly. | Medium | High | High | Test state export, integration flow, and small connection steps early. | Use a stable exported-state path or simplified integration for the final demo. | Abdullah / Shafan | Managed | Integration checks and demo tests | Frontend-backend dependency risk
R-04 | Rule Consistency | Python rules and Unity gameplay behaviour may become inconsistent. | Medium | High | High | Use shared interpreted rules and validate important scenarios across systems. | Use backend as source of truth and re-check edge cases manually. | Shafan / Abdullah | Managed | Manual parity checks and tests | Important for AI/game correctness
R-05 | Hardware / Compute | Training RL models may be slowed by limited hardware or compute power. | Medium | Medium | Medium | Use efficient training settings and rely on available cloud/GPU options when needed. | Reduce training scale or use best already-trained model for presentation. | Shafan | Managed | Training performance observations | Resource-related risk
R-06 | Code / Data Loss | Files, code, or documents may be lost because of errors or crashes. | Low | High | Medium | Use GitHub, regular saves, and organised file storage. | Restore from version history or backups. | All Team Members | Managed | Version control and file backups | Standard project safeguard
R-07 | Testing Coverage | Testing may focus too much on code and miss gameplay, UI, or integration issues. | Medium | Medium | Medium | Use both automated and broader project-level testing. | Add targeted manual checks before demo and final review. | Ahmed / Abdullah / Shafan | Managed | Test plan and review meetings | Balanced testing needed
R-08 | Documentation Load | Large number of required documents may create pressure and inconsistency. | High | Medium | High | Prepare documents gradually and align them with project work as it happens. | Prioritise compulsory evidence first and simplify low-value extras. | Ahmed | Managed | Document review and checklist | High admin workload
R-09 | Team Coordination | Miscommunication may delay tasks or create duplicated effort. | Medium | Medium | Medium | Use communication plan, regular check-ins, and role clarity. | Reassign tasks quickly and confirm decisions in writing. | All Team Members | Managed | Meetings and communication records | Reduced through planning
R-10 | Scope Creep | Extra features may be added and distract from the core project goals. | Medium | Medium | Medium | Stay aligned with charter scope and milestone priorities. | Drop non-essential extras and keep focus on core RL game delivery. | All Team Members | Managed | Scope checks against charter | Protects delivery quality
R-11 | Demo Failure | The prototype may show bugs or fail during final presentation. | Medium | High | High | Rehearse the demo, test the final build, and keep evidence ready. | Use backup video/screenshots and a stable scenario path if live demo has issues. | Ahmed / Abdullah / Shafan | Managed | Final rehearsal and demo checklist | Presentation risk
R-12 | Evaluation Evidence | Claims about results may be weak if not supported by evidence. | Medium | Medium | Medium | Keep screenshots, test outputs, metrics, and documentation organised. | Use available automated results and observed test evidence in reports. | Ahmed | Managed | Evidence collection and report review | Important for marking