## Sprint Backlog
Sprint Backlog – Gaming with RL Feature
Project Title |  |  | Core Team |  |  | Backlog Scope
Gaming with RL Feature |  |  | Shafan, Abdullah, Ahmed |  |  | Weekly sprint tasks, outputs, and milestone alignment
Sprint ID | Source File | Sprint Focus | User Story | Story Points | Shafan Tasks | Abdullah Tasks | Ahmed Tasks | Sprint Output | Milestone / Phase | Status
SB-01 | Book2.xlsx | Project kickoff | As a project team, we want to define the game problem and RL objective so that development starts with a clear direction. | 3 | Define RL problem statement ¦ Set initial success criteria | Sketch UI direction ¦ Identify player flow | Start project documentation ¦ Capture objectives and scope | Project start pack ¦ Initial problem statement | Game Design & Environment Setup | Planned / Recorded
SB-02 | Book4.xlsx | Gather requirements | As a development team, we want to gather and structure project requirements so that the solution scope is realistic and traceable. | 5 | Define RL requirements ¦ Plan environment inputs/outputs | List UI requirements ¦ Plan layout and interaction | Document requirements ¦ Structure main report sections | Requirements draft ¦ System outline | Game Design & Environment Setup | Planned / Recorded
SB-03 | Book5.xlsx | Scope finalization | As stakeholders, we want a clearly agreed project scope and initial backlog so that priorities are set early. | 5 | Define RL scope ¦ Prioritise AI tasks list | Define Unity scope ¦ Prioritise UI tasks | Compile documentation scope ¦ Prepare backlog notes | Final scope ¦ Product backlog | Game Design & Environment Setup | Planned / Recorded
SB-04 | Book6.xlsx | Research | As the team, we want to research RL methods, Unity tools, and documentation needs so that later development is evidence-based. | 5 | Research RL algorithms ¦ Compare environment needs | Research Unity tools ¦ Select supporting systems | Document research findings ¦ Consolidate references | Research notes ¦ Requirements document | Game Design & Environment Setup | Planned / Recorded
SB-05 | Book7.xlsx | UI Design | As end users, we want the game interface concept to be clear so that the final game is understandable and usable. | 3 | Align RL with UI | Final UI design | Document UI | Final UI | Game Design & Environment Setup | Planned / Recorded
SB-06 | Book8.xlsx | UI Design | As players, we want the UI design refined and aligned with the AI flow so that gameplay feels consistent. | 3 | Align RL with UI | Final UI design | Document UI | Final UI | Game Design & Environment Setup | Planned / Recorded
SB-07 | Book9.xlsx | Architecture | As developers, we want the architecture and toolchain defined so that Unity, Python, and RL components work together. | 8 | Design RL architecture ¦ Prepare RL toolchain | Plan Unity structure ¦ Configure Unity tools | Document system architecture ¦ Record setup decisions | Architecture approved ¦ Tools ready | Game Design & Environment Setup | Planned / Recorded
SB-08 | Book10.xlsx | Setup environment | As the project team, we want the development environments set up so that implementation can begin without blockers. | 5 | RL setup | Unity project setup | Documentation setup | Ready environment | Game Design & Environment Setup | Planned / Recorded
SB-09 | Book11.xlsx | Development start | As players, we want the first working prototype so that core gameplay and AI concepts can be demonstrated. | 8 | Create RL baseline components | Build initial UI/gameplay components | Draft testing approach and evidence log | Prototype build | RL Model Development | Planned / Recorded
SB-10 | Book12.xlsx | Development | As the AI developer, we want RL training and UI integration started so that the system begins to function end-to-end. | 8 | RL training | UI integration | Initial testing | Core module | RL Model Development | Planned / Recorded
SB-11 | Book13.xlsx | Debugging | As developers, we want bugs in the RL logic and UI fixed so that the core system becomes stable enough for testing. | 5 | Fix RL issues | Fix UI bugs | Testing & docs | Stable core | RL Model Development | Planned / Recorded
SB-12 | Book14.xlsx | Planning | As the team, we want to review progress and plan improvements so that the next development cycle is focused. | 3 | RL improvements | UI improvements | Update docs | Plan ready | RL Model Development | Planned / Recorded
SB-13 | Book15.xlsx | Development | As users, we want improved gameplay and AI behaviour so that the prototype becomes more reliable and useful. | 5 | Improve RL | Enhance UI | Testing | Feature update | RL Model Development | Planned / Recorded
SB-14 | Book16.xlsx | Integration | As stakeholders, we want the RL model and Unity game integrated so that the complete solution works as one system. | 8 | Integrate RL logic with game flow | Integrate Unity scenes, scripts, and API links | Run integration testing ¦ Record issues | Integrated system build | RL Model Development | Planned / Recorded
SB-15 | Book17.xlsx | Testing | As testers, we want a stable version to verify so that performance and defects can be assessed properly. | 5 | RL debugging | UI fixes | System testing | Stable version | Testing & Performance Tuning | Planned / Recorded
SB-16 | Book18.xlsx | Development | As players, we want better performance and smoother interaction so that the prototype is easier to use and evaluate. | 5 | RL optimization | UI improvement | Performance testing | Improved system | Testing & Performance Tuning | Planned / Recorded
SB-17 | Book19.xlsx | Optimization | As the team, we want to optimise AI and Unity behaviour so that the build performs better under testing. | 8 | RL tuning | Unity optimization | Metrics setup | Optimized build | Testing & Performance Tuning | Planned / Recorded
SB-18 | Book20.xlsx | Testing | As evaluators, we want full testing and validation completed so that the prototype can be judged fairly. | 5 | RL validation | UI fixes | Full testing | Tested system | Testing & Performance Tuning | Planned / Recorded
SB-19 | Book21.xlsx | Debugging | As developers, we want the remaining RL and UI errors removed so that the system is ready for refinement. | 5 | Fix RL errors | Fix UI issues | Evaluation metrics | Stable system | Testing & Performance Tuning | Planned / Recorded
SB-20 | Book22.xlsx | Refinement | As stakeholders, we want the system refined and documented so that the project is presentation-ready. | 3 | RL tuning | UI polish | Documentation | Refined system | Testing & Performance Tuning | Planned / Recorded
SB-21 | Book23.xlsx | Testing | As testers, we want validation against requirements so that final quality issues are identified before submission. | 5 | RL validation | UI validation | System testing | Stable build | Testing & Performance Tuning | Planned / Recorded
SB-22 | Book24.xlsx | Testing | As the team, we want a final technical check and testing report so that evidence is ready for assessment. | 3 | Run final RL checks and bug fixes | Complete final UI fixes and cleanup | Prepare testing report and evidence | Final tested system | Testing & Performance Tuning | Planned / Recorded
SB-23 | Book25.xlsx | Documentation | As assessors, we want the RL, UI, and documentation sections drafted clearly so that the report shows full project progress. | 5 | RL section | UI section | Main report | Draft report | UI / Documentation Consolidation | Planned / Recorded
SB-24 | Book26.xlsx | Documentation | As stakeholders, we want the full technical report and visuals completed so that the project can be communicated professionally. | 5 | Technical details | UI visuals | Final report | Full report | UI / Documentation Consolidation | Planned / Recorded
SB-25 | Book27.xlsx | Final fixes | As end users, we want the last RL fixes and UI polish so that the final build is clean and demo-ready. | 3 | RL fixes | UI polish | Edit docs | Near final | Final Report, Demo & Submission | Planned / Recorded
SB-26 | Book28.xlsx | Testing | As the team, we want the final system tested and evaluated so that we can submit with confidence. | 3 | RL final test | UI check | Evaluation | Final system | Final Report, Demo & Submission | Planned / Recorded
SB-27 | Book29.xlsx | Final review | As the project group, we want a final review and submission check so that all deliverables are complete and aligned. | 2 | Run end-to-end system review | Complete last UI and integration check | Submit final report and paperwork | Submission package | Final Report, Demo & Submission | Planned / Recorded