## Sprint Plan
Gaming with RL Feature - Sprint Plan
Sprint ID | Start Date | End Date | Phase | Sprint Goal | Shafan (RL / Logic / Testing) | Abdullah (Unity / UI / Integration) | Ahmed (Docs / Testing / Evaluation) | Planned Output | Status
Sprint 1 | 2025-09-27 | 2025-10-03 | Project Initiation & Planning | Project kickoff; Define objectives | Define RL idea ¦ Define RL problem | Brainstorm UI concept ¦ UI direction ideas | Start documentation ¦ Document objectives | Project start ¦ Problem statement | Planned
Sprint 2 | 2025-10-04 | 2025-10-10 | Project Initiation & Planning | Gather requirements; System planning | Define RL requirements ¦ RL environment planning | UI requirements ¦ UI planning | Document requirements ¦ Structure document | Requirement draft ¦ System outline | Planned
Sprint 3 | 2025-10-11 | 2025-10-17 | Project Initiation & Planning | Scope finalization; Backlog creation | RL scope ¦ RL tasks list | UI scope ¦ UI tasks list | Document scope ¦ Compile backlog | Final scope ¦ Product backlog | Planned
Sprint 4 | 2025-10-18 | 2025-10-24 | Project Initiation & Planning | Research; Requirements | RL model research ¦ RL requirements | Unity tools research ¦ System tools | Document research ¦ Final documentation | Research doc ¦ Requirements doc | Planned
Sprint 5 | 2025-10-25 | 2025-10-31 | Project Initiation & Planning | UI Design | Align RL with UI | Final UI design | Document UI | Final UI | Planned
Sprint 6 | 2025-11-01 | 2025-11-07 | Game Design & Environment Setup | UI Design | Align RL with UI | Final UI design | Document UI | Final UI | Planned
Sprint 7 | 2025-11-08 | 2025-11-14 | Game Design & Environment Setup | Architecture; Tools | RL architecture ¦ Setup RL tools | Unity planning ¦ Setup Unity tools | Document system ¦ Document setup | Architecture ¦ Tools ready | Planned
Sprint 8 | 2025-11-15 | 2025-11-21 | Game Design & Environment Setup | Setup environment | RL setup | Unity project setup | Documentation setup | Ready environment | Planned
Sprint 9 | 2025-11-22 | 2025-11-28 | RL Model Development | Development start | RL base | UI implementation | Testing plan | Prototype | Planned
Sprint 10 | 2025-11-29 | 2025-12-05 | RL Model Development | Development | RL training | UI integration | Initial testing | Core module | Planned
Sprint 11 | 2025-12-06 | 2025-12-12 | RL Model Development | Debugging | Fix RL issues | Fix UI bugs | Testing & docs | Stable core | Planned
Sprint 12 | 2025-12-13 | 2025-12-19 | RL Model Development | Planning | RL improvements | UI improvements | Update docs | Plan ready | Planned
Sprint 13 | 2025-12-20 | 2025-12-26 | RL Model Development | Development | Improve RL | Enhance UI | Testing | Feature update | Planned
Sprint 14 | 2025-12-27 | 2026-01-02 | RL Model Development | Integration | RL integration | Unity integration | Testing | Integrated system | Planned
Sprint 15 | 2026-01-03 | 2026-01-09 | RL Model Development | Testing | RL debugging | UI fixes | System testing | Stable version | Planned
Sprint 16 | 2026-01-10 | 2026-01-16 | Testing & Performance Tuning | Development | RL optimization | UI improvement | Performance testing | Improved system | Planned
Sprint 17 | 2026-01-17 | 2026-01-23 | Testing & Performance Tuning | Optimization | RL tuning | Unity optimization | Metrics setup | Optimized build | Planned
Sprint 18 | 2026-01-24 | 2026-01-30 | Testing & Performance Tuning | Testing | RL validation | UI fixes | Full testing | Tested system | Planned
Sprint 19 | 2026-01-31 | 2026-02-06 | Testing & Performance Tuning | Debugging | Fix RL errors | Fix UI issues | Evaluation metrics | Stable system | Planned
Sprint 20 | 2026-02-07 | 2026-02-13 | Testing & Performance Tuning | Refinement | RL tuning | UI polish | Documentation | Refined system | Planned
Sprint 21 | 2026-02-14 | 2026-02-20 | Testing & Performance Tuning | Testing | RL validation | UI validation | System testing | Stable build | Planned
Sprint 22 | 2026-02-21 | 2026-02-27 | Testing & Performance Tuning | Testing | Final RL check | Final UI fixes | Testing report | Final system | Planned
Sprint 23 | 2026-02-28 | 2026-03-06 | Testing & Performance Tuning | Documentation | RL section | UI section | Main report | Draft report | Planned
Sprint 24 | 2026-03-07 | 2026-03-13 | UI & Visualisation | Documentation | Technical details | UI visuals | Final report | Full report | Planned
Sprint 25 | 2026-03-14 | 2026-03-20 | UI & Visualisation | Final fixes | RL fixes | UI polish | Edit docs | Near final | Planned
Sprint 26 | 2026-03-21 | 2026-03-27 | Final Report, Demo & Submission Prep | Testing | RL final test | UI check | Evaluation | Final system | Planned
Sprint 27 | 2026-03-28 | 2026-04-03 | Final Report, Demo & Submission Prep | Final review | System check | UI check | Submit report | Submission | Planned

## Milestones
Charter Milestones and Phase Alignment
Phase | Start Date | End Date | Purpose | Main Deliverable | Notes
Project Initiation & Planning | 2025-09-27 | 2025-10-30 | Kick-off, objectives, requirements, early planning | Planning foundations completed | Built from early weekly sprint files
Game Design & Environment Setup | 2025-10-31 | 2025-11-20 | Initial game concept, design direction and environment setup | Environment ready and concept defined | Matches charter milestone
RL Model Development | 2025-11-21 | 2026-01-05 | Develop RL model and connect with game logic | RL prototype and core module | Matches charter milestone
Testing & Performance Tuning | 2026-01-06 | 2026-02-28 | Debug, refine, optimise and validate system | Stable tested prototype | Matches charter milestone
UI & Visualisation | 2026-03-01 | 2026-03-20 | Polish Unity interface and improve user-facing visuals | Refined interface and visualisation | Matches charter milestone
Final Report, Demo & Submission Prep | 2026-03-21 | 2026-04-03 | Final checks, final report, demo preparation and submission | Final delivery pack prepared | Matches charter milestone

## Team Roles
Team Responsibilities Used in the Sprint Plan
Team Member | Primary Role | Detailed Contribution | Agile Relevance
Shafan Shafqat | RL Agent and Core Logic Lead | Built the RL agent, set up the Q-learning and DQN environments, handled game logic and rules, and tested classes and functions. | Backlog refinement, technical implementation, defect fixing, sprint execution
Abdullah Butt | Unity Design and Integration Lead | Handled Unity design and Unity coding, set up the environment for the Unity design and integration, and coded the full playable game in Unity/C#. | Frontend delivery, integration tasks, UI backlog items, demo readiness
Ahmed Saeed | Documentation, Testing and Evaluation Lead | Supported Unity setup, handled documentation and paperwork, supported testing and evaluation, and managed most evaluation metrics. | Sprint evidence, reporting, QA support, evaluation and closure activities