## Retrospective Summary
Sprint Retrospective – Gaming with RL Feature
Area | What Went Well | What Was Challenging | What Was Improved | Owner / Lead | Final Status | % Complete | Notes
Project Planning | Charter, budget, backlog, sprint planning, and role allocation were created clearly. | Keeping many agile documents aligned took time. | Planning documents were standardised and organised well. | Ahmed / Shafan | Completed | 100% | Good PM foundation
Game Logic & Rules | Backend rules and logic were developed in a structured way. | Game-rule interpretation and edge cases needed careful checking. | Logic was tested and refined through code validation. | Shafan | Completed | 100% | Core system stable
RL Development | Q-learning and DQN environments were successfully set up and evaluated. | Training complexity and model tuning required patience and iteration. | A practical AI workflow was achieved and documented. | Shafan | Completed | 100% | AI side delivered
Unity Development | Playable Unity environment and coding were completed. | Frontend adjustments and integration coordination took repeated refinement. | Visual/gameplay flow improved over time. | Abdullah | Completed | 100% | Frontend complete
Testing & Evaluation | Automated and project-level testing improved project confidence. | Testing needed to cover both backend logic and gameplay behaviour. | A broader test plan and stronger evidence base were created. | Ahmed / Shafan / Abdullah | Completed | 100% | Testing completed
Documentation & Presentation | Documentation was kept moving throughout the project. | Large number of required files created workload pressure. | Reports and evidence were completed in a more organised way. | Ahmed | Completed | 100% | Submission-ready

## Sprint Review Log
Sprint Review Log
Sprint | Project Phase | Main Focus | What Went Well | Challenges | Lessons Learned | Improvement Action | Lead | Status | Comment
Sprint 1 | Initiation & Planning | Project charter, scope, roles, and milestones | Team roles were clarified early and the project direction became clear. | Initial planning required aligning several academic requirements. | Starting with planning reduces later confusion. | Keep a single reference set of project dates and milestones. | Ahmed / Shafan | Completed | Strong planning start
Sprint 2 | Research & Design | Game rules, RL research, Unity research, architecture planning | Research topics were divided logically across the team. | Connecting research areas into one design story took effort. | Design-first work helps implementation quality. | Continue linking research directly to deliverables. | All Team Members | Completed | Design phase productive
Sprint 3 | Python Backend Setup | Board, game logic, rules, and class structure | Backend structure became clear and reusable. | Rule interpretation needed careful validation. | Complex board games need early rule testing. | Document edge cases as soon as they are found. | Shafan | Completed | Core backend established
Sprint 4 | RL Environment Build | Environment state, actions, rewards, training setup | Q-learning/DQN environment setup progressed well. | Reward shaping and environment behaviour needed refinement. | AI projects need repeated small validation steps. | Test state/action logic before long training runs. | Shafan | Completed | AI pipeline foundation done
Sprint 5 | Unity Development | Gameplay view, controls, board setup, interaction | Unity-side development moved the project closer to a usable prototype. | Matching backend behaviour with frontend behaviour required care. | Frontend and backend parity is critical. | Keep integration assumptions written down clearly. | Abdullah | Completed | Frontend progressed well
Sprint 6 | Integration | Python-Unity connection and gameplay support | State export and game flow support were achieved. | Integration bugs and coordination across modules took time. | Integration should begin earlier when possible. | Introduce small integration checks every sprint in future. | Abdullah / Shafan | Completed | Key milestone completed
Sprint 7 | Testing | Automated tests, manual checks, evaluation metrics | Formal pytest testing gave strong confidence in backend rules. | Testing had to expand beyond code to gameplay and UI quality. | A full project needs different testing types, not only unit tests. | Build broader test evidence earlier. | Ahmed / Shafan / Abdullah | Completed | Testing quality improved
Sprint 8 | Documentation | Reports, charts, planning files, evidence collection | Documentation was kept organised and linked to project work. | Paperwork volume created pressure near final stages. | Building documentation gradually is better than leaving it late. | Continue writing evidence alongside development. | Ahmed | Completed | Documentation completed
Sprint 9 | Quality & Review | Refinement, review, consistency, presentation prep | The project became more polished through review activities. | Final consistency checks across files took time. | Quality control must include both technical and document outputs. | Use a final checklist for all deliverables. | Ahmed / All Team Members | Completed | Review phase successful
Sprint 10 | Final Delivery | Submission readiness and presentation/demo readiness | The project reached a completed state across major deliverables. | Final-stage time pressure remained a challenge. | Good structure earlier makes final delivery smoother. | Keep earlier checkpoints in future projects. | All Team Members | Completed | Project ready