## Status Report
Status Report – Gaming with RL Feature
Status ID | Work Area | Task / Deliverable | Owner(s) | Planned Outcome | Current Status | % Complete | Evidence / Output | Remarks | Completion State
SR-01 | Project Initiation | Project Charter prepared and revised | Ahmed / Shafan | Clear project scope, aims, milestones, stakeholders, and risks documented | Completed | 100% | Project Charter | Final planning base prepared | Done
SR-02 | Budget Planning | Budget report prepared and aligned with project needs | Ahmed | Structured cost estimation with revised budget values | Completed | 100% | Budget Report | Budget planning completed | Done
SR-03 | Agile Planning | Product backlog created | Shafan / Ahmed | Backlog items organised with priorities and story points | Completed | 100% | Product Backlog | Backlog finalised | Done
SR-04 | Agile Planning | Sprint backlog created | Shafan / Ahmed | Sprint tasks broken into actionable items | Completed | 100% | Sprint Backlog | Sprint task list completed | Done
SR-05 | Agile Planning | Sprint plan prepared | Shafan / Ahmed | Sprint schedule mapped to project timeline | Completed | 100% | Sprint Plan | Sprint structure completed | Done
SR-06 | Team Management | RACI chart prepared | Ahmed | Roles and responsibilities clearly defined | Completed | 100% | RACI Chart | Responsibility mapping completed | Done
SR-07 | Communication | Communication plan prepared | Ahmed | Communication channels, frequency, and owners documented | Completed | 100% | Communication Plan | Communication process completed | Done
SR-08 | Research | Research planning and topic division completed | All Team Members | Research areas allocated across team members | Completed | 100% | Research Plan / research notes | Research planning completed | Done
SR-09 | Game Logic | Python game rules and game logic implemented | Shafan | Functional backend logic for Origins game | Completed | 100% | Python source files | Core game logic done | Done
SR-10 | RL Development | Q-learning and DQN environment setup completed | Shafan | RL environment and training setup created | Completed | 100% | RL codebase / models | RL setup done | Done
SR-11 | Unity Development | Unity environment design and coding completed | Abdullah | Playable Unity-side game environment created | Completed | 100% | Unity project | Unity implementation done | Done
SR-12 | Integration | Python–Unity integration work completed | Abdullah / Shafan | Backend and gameplay flow connected for project needs | Completed | 100% | Integrated project build | Integration completed | Done
SR-13 | Documentation | Documentation and paperwork completed | Ahmed | Reports, planning documents, and supporting paperwork prepared | Completed | 100% | Project documents | Documentation completed | Done
SR-14 | Testing | Automated tests executed successfully | Shafan / Ahmed | Formal code-based validation completed | Completed | 100% | 23/23 pytest tests passed | Automated testing completed | Done
SR-15 | Testing | Manual / project-level testing and evaluation completed | Ahmed / Abdullah / Shafan | Gameplay, integration, and evaluation checks completed | Completed | 100% | Test Plan / evaluation evidence | Testing phase completed | Done
SR-16 | Quality | Quality review activities completed | Ahmed / All Team Members | Project outputs checked for consistency and readiness | Completed | 100% | Quality review records | Quality checks completed | Done
SR-17 | Presentation Prep | Presentation and demo preparation completed | Ahmed / All Team Members | Slides, speaking flow, and demo preparation completed | Completed | 100% | Presentation files / demo plan | Presentation prep completed | Done
SR-18 | Overall Delivery | Project deliverables completed for final submission stage | All Team Members | Project ready across planning, development, testing, and reporting | Completed | 100% | Full project package | Final delivery status complete | Done
Milestone Completion Summary
Milestone | Description | Status | % Complete | Comment
Game Design and Environment Setup | Initial game concept, design setup, and environment preparation | Completed | 100% | Finished
RL Model Development | RL setup, environment design, and learning model work | Completed | 100% | Finished
Testing and Performance Tuning | Automated and project-level testing with evaluation | Completed | 100% | Finished
User Interface and Visualization | Unity-side visuals, interaction, and UI work | Completed | 100% | Finished
Final Report, Presentation, and Demo Preparation | Documentation and final presentation readiness | Completed | 100% | Finished