## Test Plan Overview
Test Plan – Gaming with RL Feature
Testing Levels Included
Level | Description | Main Focus | Lead | Support | Status | Evidence | Notes
Unit Testing | Automated verification of Python functions and rules using pytest. | Game, rules, environment, export | Shafan | Ahmed | Completed | 23/23 pytest pass | Core formal testing already done
Integration Testing | Check that Python game state and exported data can support Unity integration. | JSON/game-state export, backend/frontend consistency | Abdullah | Shafan | Completed | Export structure checks | Supports Unity gameplay connection
Manual Gameplay Testing | Play through game scenarios to check selections, moves, turns, and expected outcomes. | Gameplay flow, move feedback, AI response | Abdullah | Ahmed | Completed | Play sessions / notes | Important for final demo
UI / UX Testing | Verify buttons, logs, labels, board rendering, and game-over displays. | Clarity and usability | Abdullah | Ahmed | Completed | Screenshots / observed issues | Useful for presentation quality
Performance / Stability Testing | Ensure the game and AI responses remain stable during repeated use. | Runtime stability and responsiveness | Ahmed | Abdullah | Completed | Runtime observations | Should be checked before demo
Regression Testing | Re-test important behaviours after code changes. | Prevent old bugs from returning | Shafan | Ahmed | Completed | Retest checklist | Important after integration changes
Demo Readiness Testing | Final end-to-end check before submission/presentation. | Submission/demo confidence | Ahmed | Shafan, Abdullah | Completed | Checklist + rehearsal | Final presentation safeguard

## Automated Pytest Tests
Automated Pytest Tests – 23 Passed
Test ID | Category | Test Name | Purpose | Board Size | Expected Result | Actual Result | Status | Lead | Support | Notes
TP-01 | Game Setup | test_game_starts_with_player_1 | Verify game starts with Player 1. | 8x8 | Current player is Player 1 | PASS | Passed | Shafan | Ahmed | Initial turn logic
TP-02 | Game Setup | test_initial_piece_positions_8x8 | Check both players start with 10 pieces each. | 8x8 | 10 pieces per player | PASS | Passed | Shafan | Ahmed | Initial board setup
TP-03 | Game Setup | test_board_has_tiles_8x8 | Ensure all 8x8 board cells have tiles. | 8x8 | No tile is None | PASS | Passed | Shafan | Ahmed | Tile presence
TP-04 | Game Setup | test_4x4_board_has_tiles | Ensure prototype board has valid tiles and element presence. | 4x4 | Tiles exist and at least one is non-neutral | PASS | Passed | Shafan | Ahmed | Prototype support
TP-05 | Move Availability | test_legal_moves_exist_for_player_1_on_8x8 | Check legal moves are available at start. | 8x8 | Legal moves > 0 | PASS | Passed | Shafan | Ahmed | Playable start state
TP-06 | Move Availability | test_legal_moves_exist_for_player_1_on_4x4 | Check legal moves on 4x4 setup. | 4x4 | Legal moves > 0 | PASS | Passed | Shafan | Ahmed | Prototype playable
TP-07 | Environment | test_4x4_environment_reset_returns_valid_state | Validate 4x4 state format. | 4x4 | Tuple length = 17 | PASS | Passed | Shafan | Ahmed | State encoding
TP-08 | Environment | test_8x8_environment_reset_returns_valid_state | Validate 8x8 state with tiles. | 8x8 | Tuple length = 129 | PASS | Passed | Shafan | Ahmed | Full state encoding
TP-09 | Environment | test_4x4_environment_returns_valid_actions | Check action list structure. | 4x4 | Non-empty list of 4-value actions | PASS | Passed | Shafan | Ahmed | Action format
TP-10 | Environment | test_4x4_environment_step_returns_correct_format | Verify step() return structure. | 4x4 | Correct tuple/dict structure | PASS | Passed | Shafan | Ahmed | RL loop format
TP-11 | Move Legality | test_illegal_move_fails | Reject illegal move and apply penalty. | 4x4 | Move fails with penalty | PASS | Passed | Shafan | Ahmed | Illegal move handling
TP-12 | Move Legality | test_human_cannot_move_within_starting_row | Prevent human move within starting row. | 8x8 | Move rejected | PASS | Passed | Shafan | Ahmed | Rule enforcement
TP-13 | Move Legality | test_human_cannot_move_backward | Prevent backward human move. | 8x8 | Move rejected | PASS | Passed | Shafan | Ahmed | Directional rule
TP-14 | Move Legality | test_human_cannot_return_to_starting_row | Prevent return to starting row. | 8x8 | Move rejected | PASS | Passed | Shafan | Ahmed | Row restriction
TP-15 | Move Legality | test_element_cannot_move_within_starting_row | Prevent element movement in starting row. | 8x8 | Move rejected | PASS | Passed | Shafan | Ahmed | Element rule
TP-16 | Element Effects | test_element_move_converts_neutral_tile | Check neutral tiles convert to element type. | 8x8 | Tiles convert correctly | PASS | Passed | Shafan | Ahmed | Tile conversion
TP-17 | Element Effects | test_element_move_captures_weaker_element_on_path | Check dominant element captures weaker element. | 8x8 | Victim removed | PASS | Passed | Shafan | Ahmed | Dominance capture
TP-18 | Element Effects | test_equal_elements_cannot_pass_each_other | Check equal elements block each other. | 8x8 | Move rejected | PASS | Passed | Shafan | Ahmed | Equal-element rule
TP-19 | Win/Loss/Draw | test_player_1_wins_when_both_humans_reach_destination | Confirm Player 1 win condition. | 8x8 | Winner = Player 1 | PASS | Passed | Shafan | Ahmed | End-game rule
TP-20 | Win/Loss/Draw | test_player_2_wins_when_both_humans_reach_destination | Confirm Player 2 win condition. | 8x8 | Winner = Player 2 | PASS | Passed | Shafan | Ahmed | End-game rule
TP-21 | Win/Loss/Draw | test_draw_when_both_players_lose_humans | Confirm draw condition. | 8x8 | Winner = None | PASS | Passed | Shafan | Ahmed | Draw logic
TP-22 | Win/Loss/Draw | test_player_wins_when_opponent_loses_humans | Confirm opponent-loss win condition. | 8x8 | Correct winner set | PASS | Passed | Shafan | Ahmed | Loss-based outcome
TP-23 | Unity Preparation | test_game_state_export | Validate exported game-state structure for Unity. | 8x8 | Required keys and dimensions valid | PASS | Passed | Shafan | Abdullah, Ahmed | Supports integration

## Additional Project Testing
Additional Project Testing Required / Planned
Test ID | Test Area | Scenario / Check | Purpose | Method | Lead | Support | Frequency | Status | Evidence | Priority | Notes
ATP-01 | Unity Integration | Check backend game-state export is read correctly by Unity. | Ensure Python and Unity communicate correctly. | Integration test / manual validation | Abdullah | Shafan, Ahmed | After export/integration changes | Completed | Screenshots / observed runs | High | Important for demo
ATP-02 | Unity Gameplay | Verify piece selection, highlighting, and valid move display work. | Ensure user interaction behaves correctly. | Manual gameplay test | Abdullah | Ahmed | Weekly / before demo | Completed | Gameplay notes / screenshots | High | Front-end usability
ATP-03 | AI Response Flow | Check AI responds after human move without crashing. | Validate human-vs-AI sequence. | Manual + observed run | Abdullah | Shafan | Weekly / before demo | Completed | Video / observation | High | Game flow stability
ATP-04 | Difficulty Modes | Test easy, normal, and hard difficulty options. | Ensure different AI modes behave as expected. | Manual gameplay test | Abdullah | Ahmed | Before final demo | Completed | Notes / comparisons | Medium | Presentation value
ATP-05 | New Game / Reset | Verify reset starts a fresh valid game state. | Ensure no stale game data remains. | Manual + integration check | Ahmed | Abdullah | Before milestone review | Completed | Observed reset results | High | Basic stability
ATP-06 | Reconnect / Server Availability | Check Unity reconnect works when Flask server is restarted. | Ensure robust demo recovery. | Manual test | Abdullah | Ahmed | Before final demo | Completed | Observed behaviour | Medium | Good backup check
ATP-07 | Manual Rule Validation | Play through key move/capture scenarios to confirm rules match expected behaviour. | Support parity between backend logic and gameplay. | Manual scenario testing | Shafan | Ahmed, Abdullah | After rule changes | Completed | Scenario checklist | High | Complements unit tests
ATP-08 | Model Evaluation | Record win rate, draw rate, and response behaviour from evaluation runs. | Support AI effectiveness claims. | Evaluation metrics review | Ahmed | Shafan | At major evaluation points | Completed | Metrics tables | High | Needed for report/demo
ATP-09 | Performance / Stability | Check for freezing, crashes, or long delays during repeated play. | Confirm prototype remains stable. | Observed runtime testing | Ahmed | Abdullah | Before final demo | Completed | Run log / notes | High | Demo readiness
ATP-10 | UI / Readability | Check board labels, logs, status messages, and buttons are readable. | Improve quality of presentation and use. | UI review | Ahmed | Abdullah | Before final presentation | Completed | Screenshots | Medium | Presentation polish
ATP-11 | Regression Retesting | Re-run important checks after code updates. | Prevent old bugs returning. | Retest checklist | Shafan | Ahmed | After major code changes | Completed | Retest record | High | Good software practice
ATP-12 | Final End-to-End Demo Test | Run complete final rehearsal with gameplay + explanation flow. | Check submission/demo confidence. | Full rehearsal | Ahmed | Shafan, Abdullah | Immediately before presentation | Completed | Checklist / video | High | Final safeguard

## Metrics and Responsibilities
Testing Metrics and Team Responsibility Balance
Metric | Value | Meaning | Owner / Main Use
Automated tests executed | 23 | Number of pytest unit tests run | Shafan / Ahmed
Automated tests passed | 23 | All formal unit tests passed | Shafan / Ahmed
Automated pass rate | 100% | Current automated testing success rate | Project-wide
Execution time | 0.19s | Fast automated execution observed in screenshot | Project-wide
Manual gameplay checks | Planned / required | Broader testing beyond code-level tests | Abdullah / Ahmed
Integration checks | Planned / ongoing | Unity-backend behaviour validation | Abdullah / Shafan
Evaluation metrics review | Required | Win rate / draw rate / performance evidence | Ahmed / Shafan
Balanced Testing Responsibility Summary
Area | Shafan | Abdullah | Ahmed | Comment
Automated Python rule tests | Lead | Support | Support | Shafan led core logic tests, with Ahmed supporting evidence and evaluation use.
Unity gameplay tests | Support | Lead | Support | Abdullah leads front-end/gameplay testing because of Unity implementation work.
Integration checks | Lead / Support | Lead | Support | Integration is shared mainly between Shafan and Abdullah.
Evaluation metrics | Support | Support | Lead | Ahmed leads metrics tracking and testing documentation.
Manual demo readiness | Support | Support | Lead | Ahmed coordinates final evidence and demo readiness with team support.
Overall testing contribution | High | High | High | Testing is represented as a shared team activity, not a single-person task.